## Sheet1
DocType_REV_ID | Entry Date | Review by | Detection version | Page/Line/Section/Entity | Open point: description of problem | Proposed Solution | Status
CRS_REV_001 | 2022-11-01 | Marwa mansour | V1.0 | Page 1/ Document history | wrong description for the change | shall mention all the new req's id | Open
CRS_REV_002 | 2022-11-01 | Marwa mansour | V1.0 | page 5/ Crs requriement ,PO_SB_CRS_009_V1.0 | wrong description for the requirement | shall be specified for premium plan and pasic plan | Open
CRS_REV_003 | 2022-11-01 | Marwa mansour | V1.0 | page 5/PO_SB_CR_MobileApp_007-V1.1 | missing requriement | shall add the microphane premission | Open
CRS_REV_004 | 2022-11-01 | Marwa mansour | V1.0 | page 5/Req from 12 to 16 | wrong format | shall change the format | Open
CRS_REV_005 | 2022-11-01 | Marwa mansour | V1.0 | page1 , document history | wrong version | shall be v.1.0 | Open
CRS_REV_006 | 2022-11-01 | Marwa mansour | V1.0 | PO_SB_CRS_011_V1.0 | the requirement shall be more specified | shall be specifed for premuiem plan only | Open
CRS_REV_007 | 2022-11-03 | Noorhan Hatem | V1.0 | PO_SB_CRS_001_V1.0 | misspelling of the word "Basic" | shall write it correctly | Open
CRS_REV_008 | 2022-11-03 | Noorhan Hatem | V1.0 | page 5 | wrong format | shall change the format | Open
CRS_REV_009 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 4 | edit the context diagram |  | Open
CRS_REV_010 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 5 | add requirments based on the change request of the CR |  | Open
CRS_REV_011 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 5 | Allow sign up with "Gmail" & "Fcebook" |  | Open
CRS_REV_012 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 5 | add reset password option |  | Open
CRS_REV_013 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 5 | Verify the accuracy of the information while logging in |  | Open
CRS_REV_014 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 5 | Prevent the duplication of email during registration |  | Open
CRS_REV_015 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 5 | app shall let users choose the plan |  | Open
CRS_REV_016 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 6 | The ride starts after the current location is determined |  | Open
CRS_REV_017 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 6 | The app shall automatically detect the current location if it has access to the location |  | Open
CRS_REV_018 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 6 | app shall allow reporting of any issue |  | Open
CRS_REV_019 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 7 | users of basic plan can upgrade to premium plan |  | Open
CRS_REV_020 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 7 | on basic plan , the icons of all saved bumbs appear on the gps screen |  | Open
CRS_REV_021 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 7 | voice notify users with the recorded speed bumbs |  | Open
CRS_REV_022 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 7 | at choosing premium plan , app shall redirect the user to the website |  | Open
CRS_REV_023 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 8 | on premium plan ,any upcoming bump shall appear on the screen |  | Open
CRS_REV_024 | 2022-11-27 | Esraa Abdelnaby | V1.2 | page 8 | The app notifies the user of the time left until the next bump |  | Open
CRS_REV_025 | 2022-11-28 | Esraa Abdelnaby | V1.2 | page 8 | by the end of the ride ,the app shall save the detected bumps |  | Open
CRS_REV_026 | 2022-11-29 | Esraa Abdelnaby | V1.2 | page 8 | The user has to give the permission to connect to the detecting device via bluetooth |  | Open
CRS_REV_027 | [6 empty] | Open
CRS_REV_028 | [6 empty] | Open
CRS_REV_029 | [6 empty] | Open
CRS_REV_030 | [6 empty] | Open
CRS_REV_031 | [6 empty] | Open